## A
UPDATING INSTRUCTIONS (Comment only - not to be printed!!)
1 | Enter PPC Number in space provided @ V7
2 | Enter date in cell V8 to which measurement relates
3 | Copy previous PPC's "Total Quantity" to "Previous Quantity" column
4 | Enter quantity of ALL work performed to date in "Qty To Date" column
5 | Any queries please ring JOHN BURKE tel: 03-9885.2899 or 0417 885 747
Contract No. |  | 12345 |  |  |  | PROGRESS PAYMENT CERTIFICATE | [5 empty] | PPC No. : | 2
Contractor |  | ACME ENGINEERING INC |  |  | This certificate is issued by the Superintendent pursuant to | [6 empty] | Period ending : | 30 Sept 2002
Title |  | EXAMPLE CONTRACT |  |  |  | the General Conditions of Contract | [5 empty] | Run Date : | 2026-07-28 10:56
We hereby certify that all statutory fees, wages and payments
as required under the Contract have been duly paid: | [6 empty] | CHECKED BY : | Civil/Struct ....................... Mech/Piping ......................... Elect/Inst ....................... Contracts Co-Ordinator ...................
SIGNED BY : Contractor ......................................................................................................... _____ /_____/200__ | [6 empty] | SIGNED FOR THE SUPERINTENDENT : ........................................................................................................................... _____/______/200__
LINE | ITEM | COST |  | EST. |  |  | CONTRACT | PREVIOUS | QUANTITY | QUANTITY | PREVIOUS | CLAIMED | CLAIMED | %
NO. | No. | CODE | DESCRIPTION OF WORK | QTY. | UNIT | RATE | TOTAL | QUANTITY | THIS PERIOD | TO DATE | CLAIM | THIS PERIOD | TO DATE | TO DATE
18 | 1 |  | PRELIMINARIES
19 | 1.01 |  | Mobilization | 100 | % | 500 | 50000 | 75 | 25 | 100 | 37500 | 12500 | 50000 | 100
20 | 1.02 |  | Demobilization | 100 | % | 250 | 25000 |  | 0 |  | 0 | 0 | 0 | 0
21 | 1.03 |  | Overheads | 100 | % | 750 | 75000 | 10 | 10 | 20 | 7500 | 7500 | 15000 | 20
22 | 1.04 |  | Initial contract detail network program | 1 | Lot | 1500 | 1500 | 1 | 0 | 1 | 1500 | 0 | 1500 | 100
23 | 1.05 |  | Updating the program in accordance
24 |  |  | with the Contract requirments | 100 | % | 150 | 15000 | 10 | 10 | 20 | 1500 | 1500 | 3000 | 20
25 | [6 empty] | - |  |  |  | - | - | - | -
26 |  |  | subtotal |  |  |  | 166500 |  |  |  | 48000 | 21500 | 69500 | 41.7417
27
28 | 2 |  | STAGE 1
29 | 2.01 |  | Demolition | 100 | % | 200 | 20000 | 75 | 25 | 100 | 15000 | 5000 | 20000 | 100
30 | 2.02 |  | Civil/Building work | 100 | % | 345 | 34500 | 75 | 5 | 80 | 25875 | 1725 | 27600 | 80
31 | 2.03 |  | Concrete | 2000 | M3 | 400 | 800000 | 800 | 700 | 1500 | 320000 | 280000 | 600000 | 75
32 | 2.04 |  | Equipment
33 | 2.04.1 |  | Platforms | 100 | % | 150 | 15000 |  | 0 |  | 0 | 0 | 0 | 0
34 | 2.04.2 |  | Balance | 100 | % | 950 | 95000 | 35 | 15 | 50 | 33250 | 14250 | 47500 | 50
35 | 2.05 |  | Pipework | 750 | M | 250 | 187500 | 75 | 110 | 185 | 18750 | 27500 | 46250 | 24.6667
36 | 2.06 |  | Insulation | 250 | M | 80 | 20000 |  | 0 |  | 0 | 0 | 0 | 0
37 | 2.07 |  | Painting | 100 | % | 200 | 20000 |  | 0 |  | 0 | 0 | 0 | 0
38 | 2.08 |  | Electrical
39 | 2.08.1 |  | Cable | 980 | M | 35 | 34300 | 98 | 147 | 245 | 3430 | 5145 | 8575 | 25
40 | 2.08.2 |  | Equipment | 100 | % | 450 | 45000 |  | 0 |  | 0 | 0 | 0 | 0
41 | 2.08.3 |  | Balance | 100 | % | 100 | 10000 |  | 0 |  | 0 | 0 | 0 | 0
42 | 2.09 |  | Instrumentation/Controls | 100 | % | 400 | 40000 |  | 0 |  | 0 | 0 | 0 | 0
43 | [6 empty] | - |  |  |  | - | - | - | -
44 | [6 empty] | 1321300 |  |  |  | 416305 | 333620 | 749925 | 56.7566
45
46 | [6 empty] | = |  |  |  | = | = | = | =
47 |  |  | TOTAL SCHEDULE "A" |  |  |  | 1487800 |  |  |  | 464305 | 355120 | 819425 | 55.0763
48
49
50 | 1 |  | Provisional Sums in accordance with Schedule "B" | 1 | Lot | 30000 | 30000 |  | 0 |  | 0 | 0 | 0 | 0
51 | [6 empty] | = |  |  |  | = | = | = | =
52 |  |  | CONTRACT SUM |  |  |  | 1517800 |  |  |  | 464305 | 355120 | 819425 | 53.9877
53
54 | SI 001 |  | Delete Provisional Sums | 1 | Lot | -30000 | -30000 |  | 0 |  | 0 | 0 | 0 | 0
55 | [6 empty] | - |  |  |  | - | - | - | -
56 |  |  | VARIATION 01 |  |  |  | -30000 |  |  |  | 0 | 0 | 0 | 0
57
58 | SI 002 |  | Replace Concrete plinth | 1 | Lot | 867.5 | 867.5 |  | 1 | 1 | 0 | 867.5 | 867.5 | 100
59 | SI 003 |  | Add Air Handling Unit | 1 | Lot | 4420 | 4420 |  | 1 | 1 | 0 | 4420 | 4420 | 100
60 | [6 empty] | - |  |  |  | - | - | - | -
61 |  |  | VARIATION 02 |  |  |  | 5287.5 |  |  |  | 0 | 5287.5 | 5287.5 | 100
62
63
64
65
66 | [6 empty] | = |  |  |  | = | = | = | =
67 |  |  | CONTRACT SUM PLUS CERTIFIED VARIATIONS |  |  |  | 1493087.5 |  |  |  | 464305 | 360407.5 | 824712.5 | 55.2354
68 | [6 empty] | = |  |  |  | = | = | = | =
69
70 | CONTRACTOR'S CASH FLOW FORECAST | [9 empty] | Total Claimed |  | 824712.5
71 | [10 empty] | Less Retention @ 10% |  | 82471.25
72 | October |  | 100000 | [7 empty] | Total Due |  | 742241.25
73 | November |  | 150000 | [7 empty] | Less Previously Certified |  | 417874.5
74 | December |  | 200000 | [9 empty] | =
75 | [10 empty] | NETT amount due |  | 324366.75
76 | [12 empty] | =